## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Wireframes and site maps are completed. Front end is being worked on. The log in page is one first pieces I’m working on. Creating accounts is finished. | 
Status as of | 26-Feb-20
Business Lead | Jim Worth
Project Manager | Daniel DeCarlo
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/19 | 
Design |  | 90% | 2/26 | 
Coding |  | 10% | 4/8 | 
SIT - System Test |  | 0% | 4/25 | 
UAT User Acceptance Test |  | 0% | 4/25 | 
Training and Doc |  | 0% | 4/23 | 
Deployment |  | 0% | 5/1 | 
Go Live |  | 0% | 5/1 | 
Hyper Care |  | 0% | 5/7 | 
# | Key Accomplishments (Current Period)
1 | Ability to create accounts is finished.
2 | Front-end coding has begun.
3 | Login Page is beginning.
# | Upcoming Activities (Next Period through (03/06/2019)
1 | Finish Login Page
2 | Start to design other sections like home page.
3 | Fix up front end design.
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Error with connecting to database with the login page. (FIXED) | Med | Med | Debug the code so the login page works. | Daniel DeCarlo | Med | 02/25
2 | Complications with styling. | Low | Med | Format the style sheet to make site appealing. | Daniel DeCarlo | Low | 
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 |  |  |  |  |  |  | 
Cairn Congregation