## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Layout began. Login page finished. On schedule with project quotes. | 
Status as of | 4-March-20
Business Lead | Jim Worth
Project Manager | Daniel DeCarlo
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/19 | 
Design |  | 90% | 2/26 | 
Coding |  | 15% | 4/8 | 
SIT - System Test |  | 0% | 4/25 | 
UAT User Acceptance Test |  | 0% | 4/25 | 
Training and Doc |  | 0% | 4/23 | 
Deployment |  | 0% | 5/1 | 
Go Live |  | 0% | 5/1 | 
Hyper Care |  | 0% | 5/7 | 
# | Key Accomplishments (Current Period)
1 | Login Page is functional and displays error and success messages.
2 | Connected donate page to cairn give.
3 | Layouts for pages are beginning.
# | Upcoming Activities (Next Period through (03/06/2019)
1 | Fix login bug.
2 | Begin edit profile.
3 | Research into searching profiles.
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Searching could take more time than expected. | Low | Med | Research enough to figure out how to avoid failures. | Daniel DeCarlo | Med | 3/18
2 | Profile editing | Med | Med | Researching how to edit profiles and update database. | Daniel DeCarlo | Med | 3/18
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 |  |  |  |  |  |  | 
Cairn Congregation