## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Error with displaying the user profile images. Table user images. Error with editing profile page. Xampp | 
Status as of | 1-April-2020
Business Lead | Jim Worth
Project Manager | Daniel DeCarlo
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 100% | 2/27 | 
Coding |  | 52% | 4/14 | 
SIT - System Test |  | 0% | 4/21 | 
UAT User Acceptance Test |  | 0% | 4/29 | 
Training and Doc |  | 15% | 5/1 | 
Deployment |  | 0% | 5/1 | 
Go Live |  | 0% | 5/1 | 
Hyper Care |  | 0% | 5/7 | 
# | Key Accomplishments (Current Period)
1 | Home Page contains carousel function.
2 | Styling for edit profile is completed.
3 | 
# | Upcoming Activities (Next Period through (03/06/2019)
1 | Get Xampp working.
2 | Continue Working on edit profile.
3 | Find a way to display the user profile image.
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Editing profile feature might take longer than expected. | Med | Med | Enter steps to resolve or minimize the risk | Daniel DeCarlo | Med | MM/DD
2 | Enter Risk 2 | Low | Med | Enter steps to resolve or minimize the risk | Daniel DeCarlo | Hi | MM/DD
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Errors with submitting and updating a users information. | Med | Med | Go through the code and debug. | Daniel DeCarlo | High | 04/8
2 | Xampp SQL server not working. | High | High | Research ways to fix and possible reinstall it. | Daniel DeCarlo | High | 4/2
Cairn Congregation