## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Xampp up and running. Update Profiles. User Manual | 
Status as of | 8-April-2020
Business Lead | Jim Worth
Project Manager | Daniel DeCarlo
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 100% | 2/27 | 
Coding |  | 70% | 4/14 | 
SIT - System Test |  | 0% | 4/21 | 
UAT User Acceptance Test |  | 0% | 4/29 | 
Training and Doc |  | 60% | 5/1 | 
Deployment |  | 0% | 5/1 | 
Go Live |  | 0% | 5/1 | 
Hyper Care |  | 0% | 5/7 | 
# | Key Accomplishments (Current Period)
1 | Updating user profiles is completed.
2 | User manual is completed. Descriptive on how to use the software.
3 | Cleaned some bugs. (With the help of Miguel).
# | Upcoming Activities (Next Period through (03/06/2019)
1 | Continue to work on uploading images for profile pictures.
2 | Add a user status function to make up for profile picture.
3 | Continue on documentation and bug issues.
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 |  |  |  |  |  |  | 
2 |  |  |  |  |  |  | 
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Profile pictures are more complicated than expected. Might remove this feature. | MED | MED | Continue researching and implement research into product. | Daniel DeCarlo | MED | 5/6
Cairn Congregation