## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Application deployed. UAT testing done. SIT done. | 
Status as of | 8-April-2020
Business Lead | Jim Worth
Project Manager | Daniel DeCarlo
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 100% | 2/27 | 
Coding |  | 100% | 4/14 | 
SIT - System Test |  | 100% | 4/21 | 
UAT User Acceptance Test |  | 100% | 4/29 | 
Training and Doc |  | 90% | 5/1 | 
Deployment |  | 100% | 5/1 | 
Go Live |  | 0% | 5/1 | 
Hyper Care |  | 0% | 5/7 | 
# | Key Accomplishments (Current Period)
1 | Application was deployed on remote desktop
2 | Users in my household tested the application and didn’t find errors.
3 | SIT is complete.
# | Upcoming Activities (Next Period through (03/06/2019)
1 | Go over feedback from presentation.
2 | Fix any bugs.
3 | Start thinking of project roadmap
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Could be bugs that UAT testers didn’t find which can be a threat to system. | Med | Med | Look at the bugs and correct them. | Daniel DeCarlo | High | 04/29
2 |  |  |  |  |  |  | 
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 |  |  |  |  |  |  | 
Cairn Congregation