## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Profile Search Results are displayed. Profile Page | 
Status as of | 18-March-2020
Business Lead | Jim Worth
Project Manager | Daniel DeCa
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 90% | 2/27 | 
Coding |  | 35% | 4/14 | 
SIT - System Test |  | 0% | 4/21 | 
UAT User Acceptance Test |  | 0% | 4/29 | 
Training and Doc |  | 0% | 5/1 | 
Deployment |  | 0% | 5/1 | 
Go Live |  | 0% | 5/1 | 
Hyper Care |  | 0% | 5/7 | 
# | Key Accomplishments (Current Period)
1 | Searching for profiles is completed.
2 | Records from the database are displayed on the search page.
3 | Personal Profile Page is beginning.
# | Upcoming Activities (Next Period through (03/06/2019)
1 | Continue working on Personal Profile pages.
2 | Editing Profile Page.
3 | Design.
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Possible issues with editing profiles and database connection | Med | Med | Research ways to reduce risk. | Daniel DeCarlo | Med | 03/25
2 | Designing | Low | Med | Research design strategies. | Daniel DeCarlo | Low | 
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
Cairn Congregation