## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Private profile display. Pictures. | 
Status as of | 25-March-2020
Business Lead | Jim Worth
Project Manager | Daniel DeCarlo
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 90% | 2/27 | 
Coding |  | 50% | 4/14 | 
SIT - System Test |  | 0% | 4/21 | 
UAT User Acceptance Test |  | 0% | 4/29 | 
Training and Doc |  | 0% | 5/1 | 
Deployment |  | 0% | 5/1 | 
Go Live |  | 0% | 5/1 | 
Hyper Care |  | 0% | 5/7 | 
# | Key Accomplishments (Current Period)
1 | Individual profile pages are completed.
2 | Upload Picture.
3 | Edit profile beginning.
# | Upcoming Activities (Next Period through (03/06/2019)
1 | Finish editing.
2 | Finish profile picture upload.
3 | Design
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Editing Profile/upload Pics | Med | Med | There could be database errors that need to be fixed. | Daniel DeCarlo | Med | 
2 | Designing | Low | Med | Research design strategies. | Daniel DeCarlo | Low | 
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Enter Issue 1 (a risk that has actually happened) |  |  | Enter steps to resolve | name |  | MM/DD
Cairn Congregation